## Sheet1
contractor: Sajjad Kaheni |  | Report sheet | Employer: PANTOhealth
Date: | 2025-03-14
Assumption 1. The start date of the project is 04/05/04 2025 2. The start day of the week is Saturday 3. Stat time is 8:00 AM 4. End time is 4:00 PM 5. Hours per day: 8 hours, Days per month: 22 days, Hours per week: 36 hours 6. Duration entered in days 7. All days start working from 8:00 until 16:00 except Wednesday (8:00 till 14:00) 8. Friday and Thursday are not working days 9. One day is non-working because of Imam Khomeini's death 06/04/2025 10. Auto schedule selected
Remark 1. I prioritized Vendor & Resource Management section over the others because procuring raw materials and coordinating with contractors must be done at the beginning, as all future activities depend on it. 2. Due to the importance of the Vendor & Resource Management section, I have defined a milestone to ensure that no other activities begin until this phase is completed. 3. Due to potential disruptions in the transportation process, the activities in the Track Bed Upgrades section will start with a two-day delay. 4. The Signal & Communication Systems task will start four days after the completion of Track Bed Upgrades due to potential weather-related issues during the track work. 5. I added the 'Permits Approved' milestone to ensure that no physical construction work begins until all necessary regulatory approvals and permits are secured. This milestone acts as a checkpoint to prevent potential legal issues and work stoppages. Any delays in obtaining permits will automatically push back dependent tasks, helping maintain compliance and project feasibility. 6. Engineers earn 2,000,000 per hour and 2,100,000 for overtime, workers earn 700,000 per hour and 800,000 for overtime, and engineers receive a 20% salary increase from 4/26/2025. 7. To avoid lengthiness, only two resources, Engineer and Worker, along with the cost of purchasing raw materials and other expenses, were defined, and the definition of "material" was omitted.